## Product backlog V1
Status
Complete
In Progress
On Hold
Not started
Product Backlog
ID No. | Epic | Sprint | User Story | Story Details | Acceptance Test Criteria | Task | Date Start | Date Finish | Story Point | Priority | Status
1 | Smart glasses using arduino board | To be Asigned | As a glass Owner I want that the device should small attached to glass so that it is easy to wear and comfotable. | Device should be small and well embedded their connection should be good and properly wraped device should not be too heavy to glasses. | 1. Device should be properly embedded and installed to the glasses. 2. components of device should be adjusted properly should not put weight on one side. | 1. Connecting all the components with device after analysing wieght management 2. Component and device should be small in size to reduce weight and increase comfortablility.
2 | Smart glasses using arduino board | To be Asigned | As a glass owner I want ON/OFF button so that I can ON/OFF my device | There should be ON/OFF to prevent battery wastage and acess to user to ON or OFF its device | 1.ON/OFF button properly work or not. 2.After Starting device it search for bluetooth device or not 3. After starting the device screen should also start. | 1. Attaching a button to device. 2. Coding to give functioning to button.
3 | Smart glasses using arduino board | To be Asigned | As a Glass owner I want clear content on screen so that it is easily viewed | Screen should be at proper position on glasses so that content is clearly viewed | 1. Content should be clearly viewed 2. Screen should be installed at proper position in glasses so that doesn't create any strain in eyes. 3. Output coding is properly done and Screen properly display the output | 1. Screen and mirror should be adjusted on glasses after studing all the angles. 2. Coding for displaying output on screen
4 | Smart glasses using arduino board | To be Asigned | As a glass owner I want screen to display date and time so that I catch my time. | device showed show date and time on screen with or without smartphone connection | 1. Screen should show right time and date. 2. device should show date and time without bluetooth connection also 3. After restarting device it should show right date and time. | 1. Coding for date and time
5 | Smart glasses using arduino board | To be Asigned | As a glass Owner I want a bluetooth connection in my device so that I can connect my smartphone with my glasses | There should be a bluetooth connection to trasfer data from smartphone to device to display on glasses screen | 1. Device should connect with the smartphone and data should be transferred easily. 2. Buetooth module should be properly installed in device 3. bluetooth connectivity coding should be properly done means data received from smartphone is encoded properly or not. | 1. Attaching bluetooth module with arduino nano board. 2.Adding code to access bluetooth connectivity and to encode that data received from smartphone 3.Pairing device with smartphone
6 | Smart glasses using arduino board | To be Asigned | As a glass owner I want notification on screen so that I can get notified | Device should show notification on screen while connected to smartphone | 1. Coding for notification is proper or not 2. call notification is visible on screen. 3. text notification is visible on screen | 1.coding for notification for call and text message.

## Product backlog V2
Status
Complete
In Progress
On Hold
Not started
Product Backlog
ID No. | Epic | Sprint | User Story | Story Details | Acceptance Test Criteria | Task | Date Start | Date Finish | Story Point | Priority | Status
1 | Smart glasses using arduino board | To be Assigned | As a User I want that the device should be small which is attached to glass so that it is easy to wear and comfotable. | Device should be small and well embedded their connection should be good and properly wraped device should not be too heavy to glasses. | 1. Device should be properly embedded and installed to the glasses. 2. components of device should be adjusted properly should not put weight on one side. | 1. Connecting all the components with device after analysing wieght management 2. Component and device should be small in size to reduce weight and increase comfortablility.
2 | Smart glasses using arduino board | To be Assigned | As a User I want ON/OFF button so that I can ON/OFF my device | There should be ON/OFF to prevent battery wastage and acess to user to ON or OFF its device | 1.ON/OFF button properly work or not. 2.After Starting device it search for bluetooth device or not 3. After starting the device screen should also start. | 1. Attaching a button to device. 2. Coding to give functioning to button.
3 | Smart glasses using arduino board | To be Assigned | As a User I want clear content on screen so that it is easily viewed | Screen should be at proper position on glasses so that content is clearly viewed | 1. Content should be clearly viewed 2. Screen should be installed at proper position in glasses so that doesn't create any strain in eyes. 3. Output coding is properly done and Screen properly display the output | 1. Screen and mirror should be adjusted on glasses after studing all the angles. 2. Coding for displaying output on screen
4 | Smart glasses using arduino board | To be Assigned | As a User I want screen to display date and time so that I catch my time. | device showed show date and time on screen with or without smartphone connection | 1. Screen should show right time and date. 2. device should show date and time without bluetooth connection also 3. After restarting device it should show right date and time. | 1. Coding for date and time
5 | Smart glasses using arduino board | To be Assigned | As a User I want a bluetooth connection in my device so that I can connect my smartphone with my glasses | There should be a bluetooth connection to trasfer data from smartphone to device to display on glasses screen | 1. Device should connect with the smartphone and data should be transferred easily. 2. Buetooth module should be properly installed in device 3. bluetooth connectivity coding should be properly done means data received from smartphone is encoded properly or not. | 1. Attaching bluetooth module with arduino nano board. 2.Adding code to access bluetooth connectivity and to encode that data received from smartphone 3.Pairing device with smartphone
6 | Smart glasses using arduino board | To be Assigned | As a User I want notification on screen so that I can get notified | Device should show notification on screen while connected to smartphone | 1. Coding for notification is proper or not 2. call notification is visible on screen. 3. text notification is visible on screen | 1.coding for notification for call and text message.
7 | Application | To be Assigned | As a User I want an application to connect my smartphone with device | An application to run in smartphone which will help to connect with device using bluetooth | 1.App must run on smartphone properly 2. It should connect with arduino board bluetooth module. 3. Its Should transfer data from smartphone to arduino board after coding data. | 1. Build a Application using Android studio. 2.App must be compatible with arduino board.
8 | Application | To be Assigned | As a User I want buttons in the app so that I can connect and disconnect from my smartphone | application GUI should represent status of conectivity and provide button to connect or disconect | 1. application must represent connection status 2. button should be properly shown on screen | 1. Build buttons in GUI for App 2. Make operational functions to make button functionable. 3. Coding in App to show status of conectivity
9 | Website | To be Assigned | As a user I want a website so that I can see about my product features and functionality. | Website should contain information about product its feature functionality how to use it effectively. | 1. There is a home page giving a brief detail about product. 2. | 1. Coding of website 2. Adding Information regarding feature and functionality
10 | Website | To be Assigned | As a user I want a webpage in website that having a guide about product so that we can use product effectively | in the webpage there should be a guide provided about product to make aware how to use it in a effective way | 1. Guide should cover all the functionality of product. 2. App tour should be available to understand the usage of Application 3. Guide should tell all the safety concerns. | 1. creating a webpage asigning it to home page. 2. adding guide information in it
11 | Website | To be Assigned | As a user I want a query form in website so that whenever there is an query related to product can consult to experts | There should be a form to take feedback from user and get there query to resolve them | 1. Feedback form is properly visible on webpage 2. After filling all the information mail is immediately sended to Organising team. 3. Form should noify that your feedback is received. | 1. creating form coding and adding it to home page 2. Creating columns for getting information
12 | Website | To be Assigned | As a user I want a link to download App so that we can use the device through smartphone | There must be a link provided in website to download apk through we can acess our device after matching the passcode with device | 1. Link acess is properly available 2. Link redirect to the right location. 3. App file availble is properly downloaded or not | .
13 | Website | To be Assigned | As a user I want a web page descibing about safety of product so that we can see about safety of product and its safe use | there must be a web page discribing about the safety of product. | 1. Content is properly visible 2. Font size and color for content must be appropriate | Creating a Web page and adding information in it
14 | Website | To be Assigned | As a user I want a webpage discribing about Organising team so that anyone can see about organizer information | Webpage giving a brief description about organizer team | 1. Content is properly visible 2. Font size and color for content must be appropriate | Creating a Web page and adding information in it
15 | Smart glasses using arduino board | To be Assigned | As a Maintainer I want comments should be added in coding so that if there is any problem it can easily be spotted | The main code of the arduino board and other components coding should contain comments so that it is easily for future to understand | 1.All the important code consist of comments 2. comments completely descibe the code | 1. Add comments for all important coding
16 | Website | To be Assigned | As a maintainer I want a manual available on website so that circuit can easily be understood | If there is any problem in device after understanding circuit diagram it can easily be resolved | 1. Device is build correctly according to circuit diagram. 2. Product Manual is available on website | 1. Add link to download Product Manual on website

## product backlog V3
STATUS
Complete
In Progress
On Hold
Not started
Status | Epic | Category | Story detail | Acceptance Test Criteria | Sprint Ready | Sprint | Story Point | Completion level | Date start | Date finish
|  | HIGH PRIORITY |  |  | -
| Smart glasses using arduino board | As a User I want a bluetooth connection in my device so that I can connect my smartphone with my glasses | There should be a bluetooth connection to trasfer data from smartphone to device to display on glasses screen | 1. Device should connect with the smartphone and data should be transferred easily. 2. Buetooth module should be properly installed in device 3. bluetooth connectivity coding should be properly done means data received from smartphone is encoded properly or not. | FALSE |  | 13 | EMPTY
|  | 1. Attaching bluetooth module with arduino nano board. |  |  | FALSE |  |  | EMPTY
|  | 2.Adding code to access bluetooth connectivity and to encode that data received from smartphone |  |  | FALSE |  |  | EMPTY
|  | 3.Pairing device with smartphone |  |  | FALSE |  |  | EMPTY
| Smart glasses using arduino board | As a User I want that the device should be small which is attached to glass so that it is easy to wear and comfotable. | Device should be small and well embedded their connection should be good and properly wraped device should not be too heavy to glasses | 1. Device should be properly embedded and installed to the glasses. 2. components of device should be adjusted properly should not put weight on one side. | FALSE |  | 13 | EMPTY
|  | 1. Connecting all the components with device after analysing wieght management |  |  | FALSE |  | 2
|  | 2. Component and device should be small in size to reduce weight and increase comfortablility. |  |  | FALSE |  | 4
| Smart glasses using arduino board | As a User I want notification on screen so that I can get notified | Device should show notification on screen while connected to smartphone | 1. Coding for notification is proper or not 2. call notification is visible on screen. 3. text notification is visible on screen | FALSE |  | 13 | EMPTY
|  | 1.coding for notification for call and text message. |  |  | FALSE
|  | MEDIUM PRIORITY |  |  | -
| Smart glasses using arduino board | As a User I want ON/OFF button so that I can ON/OFF my device | There should be ON/OFF to prevent battery wastage and acess to user to ON or OFF its device | 1.ON/OFF button properly work or not. 2.After Starting device it search for bluetooth device or not 3. After starting the device screen should also start. |  |  | 8 | EMPTY
1. Attaching a button to device.
2. Coding to give functioning to button.
| Smart glasses using arduino board | As a User I want clear content on screen so that it is easily viewed | Screen should be at proper position on glasses so that content is clearly viewed | 1. Content should be clearly viewed 2. Screen should be installed at proper position in glasses so that doesn't create any strain in eyes. 3. Output coding is properly done and Screen properly display the output |  |  | 8 | EMPTY
1. Screen and mirror should be adjusted on glasses after studing all the angles.
2. Coding for displaying output on screen
| Smart glasses using arduino board | As a User I want screen to display date and time so that I catch my time. | device showed show date and time on screen with or without smartphone connection | 1. Screen should show right time and date. 2. device should show date and time without bluetooth connection also 3. After restarting device it should show right date and time. |  |  | 8 | EMPTY
1. Coding for date and time
| Website | As a user I want a website so that I can see about my product features and functionality. | Website should contain information about product its feature functionality how to use it effectively. | 1. There is a home page giving a brief detail about product. |  |  | 5 | EMPTY
1. Coding of website
2. Adding Information regarding feature and functionality
| Website | As a user I want a query form in website so that whenever there is an query related to product can consult to experts | There should be a form to take feedback from user and get there query to resolve them | 1. Feedback form is properly visible on webpage 2. After filling all the information mail is immediately sended to Organising team. 3. Form should noify that your feedback is received. |  |  | 5 | EMPTY
1. creating form coding and adding it to home page
2. Creating columns for getting information
| Smart glasses using arduino board | As a Maintainer I want comments should be added in coding so that if there is any problem it can easily be spotted | The main code of the arduino board and other components coding should contain comments so that it is easily for future to understand | 1.All the important code consist of comments 2. comments completely descibe the code |  |  | 3 | EMPTY
1. Add comments for all important coding
|  | LOW PRIORITY |  |  | -
| Website | As a user I want a webpage in website that having a guide about product so that we can use product effectively | in the webpage there should be a guide provided about product to make aware how to use it in a effective way | 1. Guide should cover all the functionality of product. 2. App tour should be available to understand the usage of Application 3. Guide should tell all the safety concerns. | TRUE |  | 3 | EMPTY
1. creating a webpage asigning it to home page.
2. adding guide information in it
| Website | As a user I want a web page describing about safety of product so that we can see about safety of product and its safe use | there must be a web page discribing about the safety of product. | 1. Content is properly visible 2. Font size and color for content must be appropriate |  |  | 3 | EMPTY
Creating a Web page and adding information in it
| Website | As a user I want a webpage discribing about Organising team so that anyone can see about organizer information | Webpage giving a brief description about organizer team | 1. Content is properly visible 2. Font size and color for content must be appropriate |  |  | 3 | EMPTY
Creating a Web page and adding information in it
| Website | As a maintainer I want a manual available on website so that circuit can easily be understood | If there is any problem in device after understanding circuit diagram it can easily be resolved | 1. Device is build correctly according to circuit diagram. 2. Product Manual is available on website |  |  | 2 | EMPTY
1. Add link to download Product Manual on website
| Website | As a user I want a link to download App so that we can use the device through smartphone | There must be a link provided in website to download apk through we can acess our device after matching the passcode with device | 1. Link acess is properly available 2. Link redirect to the right location. 3. App file availble is properly downloaded or not |  |  | 1 | EMPTY
Uploading apk on cloud and providing its link in website
COMPIETION LEVEL
HALF
EMPTY
COMPLETE
THREE QUARTER

## Sprint Backlog
STATUS
Complete
In Progress
On Hold
Not started
SPRINT BACKLOG
Status | Epic | Category | Story detail | Story Point | Priority | Assigned To:- | Completion level | Date start | Date finish | Duration | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total Estimation Hour
|  | SPRINT 1 |  | 26 | [16 empty] | 10
| Smart glasses using arduino board | As a User I want a bluetooth connection in my device so that I can connect my smartphone with my glasses | There should be a bluetooth connection to trasfer data from smartphone to device to display on glasses screen | 13 | LOW |  | 0% | [13 empty] | 5
|  | 1. Attaching bluetooth module with arduino nano board. |  |  |  |  | 0%
|  | 2.Adding code to access bluetooth connectivity and to encode that data received from smartphone |  |  |  |  | 0%
|  | 3.Pairing device with smartphone |  |  |  |  | 0%
| Smart glasses using arduino board | As a User I want that the device should be small which is attached to glass so that it is easy to wear and comfotable. | Device should be small and well embedded their connection should be good and properly wraped device should not be too heavy to glasses | 13 | HIGH |  | 0% | [13 empty] | 5
|  | 1. Connecting all the components with device after analysing wieght management |  |  |  |  | 0%
|  | 2. Component and device should be small in size to reduce weight and increase comfortablility. |  |  |  |  | 0%
|  | SPRINT 2 |  | 21 | [16 empty] | 9
| Smart glasses using arduino board | As a User I want notification on screen so that I can get notified | Device should show notification on screen while connected to smartphone | 13 | [16 empty] | 5
1.coding for notification for call and text message.
| Smart glasses using arduino board | As a User I want screen to display date and time so that I catch my time. | device showed show date and time on screen with or without smartphone connection | 8 | [16 empty] | 4
1. Coding for date and time
|  | SPRINT 3 |  | 16 | [16 empty] | 6
| Smart glasses using arduino board | As a User I want ON/OFF button so that I can ON/OFF my device | There should be ON/OFF to prevent battery wastage and acess to user to ON or OFF its device | 8 | [16 empty] | 3
1. Attaching a button to device.
2. Coding to give functioning to button.
| Smart glasses using arduino board | As a User I want clear content on screen so that it is easily viewed | Screen should be at proper position on glasses so that content is clearly viewed | 8 | [16 empty] | 3
1. Screen and mirror should be adjusted on glasses after studing all the angles.
2. Coding for displaying output on screen
|  | SPRINT 4 |  | 13 | [16 empty] | 5
| Smart glasses using arduino board | As a Maintainer I want comments should be added in coding so that if there is any problem it can easily be spotted | The main code of the arduino board and other components coding should contain comments so that it is easily for future to understand | 3 | [16 empty] | 1
1. Add comments for all important coding
| Website | As a user I want a website so that I can see about my product features and functionality. | Website should contain information about product its feature functionality how to use it effectively. | 5 | [16 empty] | 2
1. Coding of website
2. Adding Information regarding feature and functionality
| Website | As a user I want a query form in website so that whenever there is an query related to product can consult to experts | There should be a form to take feedback from user and get there query to resolve them | 5 | [16 empty] | 2
1. creating form coding and adding it to home page
2. Creating columns for getting information
|  | SPRINT 5 |  | 12 | [16 empty] | 4
| Website | As a user I want a webpage in website that having a guide about product so that we can use product effectively | in the webpage there should be a guide provided about product to make aware how to use it in a effective way | 3 | [16 empty] | 1
1. creating a webpage asigning it to home page.
2. adding guide information in it
| Website | As a user I want a web page describing about safety of product so that we can see about safety of product and its safe use | there must be a web page discribing about the safety of product. | 3 | [16 empty] | 1
Creating a Web page and adding information in it
| Website | As a user I want a webpage discribing about Organising team so that anyone can see about organizer information | Webpage giving a brief description about organizer team | 3 | [16 empty] | 1
Creating a Web page and adding information in it
| Website | As a maintainer I want a manual available on website so that circuit can easily be understood | If there is any problem in device after understanding circuit diagram it can easily be resolved | 2 | [16 empty] | 0.7
1. Add link to download Product Manual on website
| Website | As a user I want a link to download App so that we can use the device through smartphone | There must be a link provided in website to download apk through we can acess our device after matching the passcode with device | 1 | [16 empty] | 0.3
Uploading apk on cloud and providing its link in website
|  | TOTAL |  | 88 | [16 empty] | 34